## Project Risk Log
PIO Risk Register A - PIO - 005
Part I. Risk Identification | [5 empty] | Part II. Risk Analysis for Existing Controls |  |  | Part III. Risk Response
Name | Project Risk Category | Risk Description (ignoring controls) | Impact 1-5 (ignoring controls) | Likelihood 1-5 (ignoring controls) | Total Risk Score Low = 1 - 8 Med = 9 - 16 High = 17 - 25 | What Controls (if any) are currently in place? | Control Effectiveness 1-5 | Residual Risk Score Low = 1 - 8 Med = 9 - 16 High = 17 - 25 | Control or Risk Mitigation Strategy | Control effectiveness based on mitigation strategy 1-5 | Residual Mitigated Risk Low = 1 - 8 Med = 9 - 16 High = 17 - 25 | Contingency Plan | Cost of contingency plan | Owner | Review Due Date | Status
Limited MTCS Participant Availability | Quality | If key Summit participants are unavailable or unable to participate then the quality of the summit's results will be adversely impacted. | 4 | 3 | 12 | n/a | 5 | 11.88 | Early communications and committments with desired participants and providing travel expenses | 3 | 6 | Select from back-up candidates | Additional staff time ~$5,000 | PM | 2019-07-01 | Open
Venue Avaialbility for MTCS | Resources | If first choice of venue (STScI) becomes unavailable for summit another location will need to be selected. | 3 | 2 | 6 | n/a | 5 | 5.94 | Early communications with STScI staff and engagement with STScI as a partner in workshop | 2 | 1.5 | Pay for venue | ~$5000 | PM | 2019-07-15 | Open
Venue Avalibility for MTMW | Quality | If first choice of venue (AAS January 2021) is not available for workshop an alternate, less optimal venue will need to be selected. | 4 | 2 | 8 | n/a | 5 | 11.1375 | Early communications with AAS Press Office and engagement with AAS as partner in workshop | 2 | 5.625 | Pay for venue | ~$2000 | PM | 2020-07-06 | Open
MMA/TDA Planetarium Program Production Costs | Scope | If contractors cannot deliver planetarium program with all scripted elements within existing budget program's scope will have to be reduced. | 4.5 | 2.5 | 11.25 | n/a | 5 | 11.1375 | Develop program script to utilize known existing and partnership resources wherever possible. | 3 | 5.625 | Expand partnerships to share production costs for animations related to featured facilities (LSST, LIGO etc.) | Up to 6-month delay with increased staff time required ~$20k | PM | 2020-06-01 | Open
Limited Staff Resouces | Resources | If one or more existing staff leave the project because of illness, turnover or internal opportunities then the project will be impacted. | 4 | 4 | 16 | n/a | 5 | 15.84 | 1) Monitor staff employment situations 2) Offer monetary incentive to keep staff | 2 | 4 | 1) Execute contract for temp employees 2) Execute staff monetary incentive | Houry rates and incentives TBD ~$5,000 | PM | Quarterly | Open

## Closed risks
MOVE CLOSED RISKS INTO THIS TAB
Part I. Risk Identification | [5 empty] | Part II. Risk Analysis for Existing Controls |  |  | Part III. Risk Response
Name | Project Risk Category | Risk Description (ignoring controls) | Impact 1-5 (ignoring controls) | Likelihood 1-5 (ignoring controls) | Total Risk Score Low = 1 - 8 Med = 9 - 16 High = 17 - 25 | What Controls (if any) are currently in place? | Control Effectiveness 1-5 | Residual Risk Score Low = 1 - 8 Med = 9 - 16 High = 17 - 25 | Control or Risk Mitigation Strategy | Control effectiveness based on mitigation strategy 1-5 | Residual Mitigated Risk Low = 1 - 8 Med = 9 - 16 High = 17 - 25 | Contingency Plan | Cost of contingency plan | Owner | Review Due Date | Status

## Grading Criteria
NOTE: Each project owns customizing this worksheet to criteria that makes sense for their project.
Impact - Scale
Impact Criteria | 1 | 2 | 3 | 4 | 5
Technology Risk | Known technology |  | Known technical foundation |  | State of the art technology
Resource Competency / availability | Competency in-house |  | Some in-house / some known external |  | Minimal to no in-house knowledge
Strategic / Telescope interruption or Competitive Disadvantage | Low Severity (Manual process could recover) |  | Medium Severity |  | High Severity or Business Stop
Schedule | Schedule well understood |  | Schedule has some unknowns |  | Schedule is not well understood
Financial loss | <=$250K |  | $250k - $5M |  | >=$5M
Scope | Scope well understood; no change requests submitted |  | Scope gaps exist in non-critical areas. Some change requests submitted or expected | N/A | Scope not well defined. Change requests inevitable
Likelihood - Scale
Likelihood Criteria | 1 | 2 | 3 | 4 | 5
Probability | 0% | 25% | 50% | 75% | 100%
Descriptive | Remote |  | Probably |  | Certain
Controls Effectiveness - Scale
| 1 | 2 | 3 | 4 | 5
Weight for calc purposes, DO NOT CHANGE | 99% | 75% | 50% | 25% | 1%
Descriptive | Existing - Sufficient |  | Existing - Non Sufficient |  | Non-Existent