## Sheet1
OBS09-006A: GeMS (Phase 3-4-5) (M. Boccas)
Name
-GeMS Project (phase 3-4-5)
-Phase 3: I&T at CP and on telescope
-Infrastructure
Support structure telescope impact characterization
LSS+LSE telescope impact characterization
SyE support for LSS+LSE charact.
ME support for LSS+LSE charact.
Full infrastructure load telescope impact characterization
SyE support fro full load charact.
caulking job on flanges
SS final painting
design and procure furniture for LSE
balance air flow system in LSE
do metrology of 6 pads to elevation axis
-LSE integration and testing on telescope
SyE LSE misc. integration on tel
ME LSE misc. integration on tel
LSE epics interface implementation
LSE AHU thermal tests
LSE AHU vibration tests
LSE integration and testing on the telescope completed (except temp)
install HW interlock to AHU
finalize LSE AT (temp control)
-GS Laser I&T on telescope
-GS Laser System integration in LSE
GS laser installed in LSE
-GS laser integration in LSE completed tasks
Gs laser documentation review
LE for laser integration in LSE
OE for laser integration in LSE
EE for laser integration in LSE
fix crystal temp controller
Implement GS laser data-logging on GEA
fabricate custom laser computer table
fabricate folding bench
review and connect clean air to laser bench volume
Finalize GS laser remote computer control access configuration
Implement GS laser automatic monthly data logging on external drive
Install new (working!) polycom in GS LSE
Develop GS laser EPICS IF DM screens
Milestone: All pending GS laser I&T tasks completed (alignment work not included)
-GS laser alignment and optimization to performance specifications
Set up LSE for final GS laser alignment
Align GS laser 1064 oscillator
Contingency to align GS laser 1064 oscillator
Align GS laser 1319 oscillator
Contingency to align GS laser 1319 oscillator
Align GS laser 1064 amplifiers
Contingency to align GS laser 1064 amplifiers
Align GS laser 1319 amplifiers
Contingency to align GS laser 1319 amplifiers
Align GS laser 589 output and diagnostics
Contingency to align GS laser 589 output and diagnostics
Cumulated remaining contingency
Milestone: GS laser at spec and ready for propagation through BTO
+GS laser spares procurement
-GS BTO I&T on telescope
-GS BTO pending phase 2 task milestones
milestone: end BTO troubleshooting phase (at zenith)
BTO motor controlled debugged
BTO LUT and offloads implemented
Final BTO AT successful
GS BTO aligned with surrogate laser at zenith, ready for elevation tests
-GS BTO optical testing vs elevation
Move telescope, create EFM LUT, implement in BTO SW, and test vs elevation
Move telescope, create TPM LUT, implement in BTO SW, and test vs elevation
Move telescope, create TCM LUT, implement in BTO SW, and test vs elevation
Move telescope, create TRA LUT, implement in BTO SW, and test vs elevation
Contingency to create BTO EFM-TPM-TCM-TRA LUTs
test E Pol control
write BTO LUT determination procedure
Milestone: BTO ready for laser
+LBBS I&T on telescope
Milestone: LBBS ready for laser propagation *at varying elevation*
+GS BTO I&T miscellaneous (not on critical path)
+GS LGSF I&T on telescope
+Telescope Cooling service
+Canopus CP lab work
Canopus CP lab work contingency
+GSAOI CP lab work (see ENG10-113 SW)
+GeMS HLS readiness (link to ENG10-113 milestones)
-Canopus + GSAOI integration on telescope
- Telescope installation
compile installation procedures
write technical procedure for canopus and GSAOI
Install Canopus on telescope [MILESTONE]
align AO fold
Canopus electro-mechanics testing on telescope
Canopus software testing on telescope
Canopus optical alignment on telescope
End integration Canopus on telescope
install GSAOI on telescope
GSAOI electronics+SW testing on telescope
coalign GSAOI-Canopus on telescope (SF fold-pupil-focus)
end GSAOI-Canopus installation on telescope
-NCPA
NCPA compensation in 1 direction
NCPA compensation in the field
NCPA automatic scheme
NCPA vs. control matrix
NCPA vs. elevation vs. CassRot
-Performance
NGS (TT and TA) loop optimization
LGS loop optimization
LGS cMat vs. Elevation
Extrapolator optimization
Full performance test
+Miscellaneous
Canopus + GSAOI on-telescope contingency
-Phase 4: telescope technical commissioning
-GS laser ops training in 2010
Read GS laser ops manual and other documentation
Prepare GS laser ops training plan
Train GS laser operator to level 1 ops during day-time
-GS LGSF night-time commissioning
+GS LGSF July 2010 telescope shutdown
-GS BTO on-sky alignment of CM-KM-PM with NGS
GS BTO on-sky alignment of CM-KM-PM with NGS: start date
GS BTO on-sky alignment of CM-KM-PM with NGS: end date
-GS BTO on-sky pre-commissioning checks with NGS: night plan
Point Gemini telescope to bright star
Align PM and CM to center NGS on BTO NF and FF diagnostic cameras
Rotate KM and characterize NGS image rotation on diagnostic cameras
Derive PM/CM LUT vs KM angle
Implement PM/CM LUT vs KM angle in BTO software and test on-sky
Contingency to remove BTOOB from LLT and realign CM-KM-PM in the lab if BTO night testing with NGS failed
Focus LLT for 589nm imaging using LLT focus knob (day-time)
Milestone: GS LGSF ready for on-sky commissioning *at zenith* WITHOUT polarization optimization
Milestone: GS LGSF ready for on-sky laser commissioning *at zenith* WITH polarization
+GS LGSF on-sky commissioning *at zenith* (run#1)
+GS LGSF on-sky commissioning *vs elevation* (run#2)
Milestone: GS LGSF usable for GeMS on-sky commissioning
LGSF ready for Canopus commissioning
+GS LGSF ops support through remainder of 2011
GeMS night-time commissioning planning
Declare MCAO-GSAOI ready for night-time
-GeMS night-time technical commissioning
-Technical run #1
acquire laser spots on LGSWFS
measure fratricide effects on WFS
close MCAO HO loop on sky
Acquire Interaction Matrix on-sky
close BTO-FSA offload loop
test offload to M1
Check FSA dithering for centroid gain optimiztion
Check High-Order stability and quick perf optim
LGS zoom calibration vs elevation
Close TT loop on 1 bright NGS
Check astrometric mode on 1 bright NGS
Test offloading to M2
GeMS tech run 1 coord+quality support
SWHL support for run1
contingency run#1
+Technical run #2
+Technical run #3
+Technical run #4 (after shutdown)
inter-run support, troubleshooting, upgrades, preps
GeMS technical commissioning run result analysis
contingency technical commissioning
Declare MCAO technical commissioning complete
+GEMS Software Science Verification Tasks
-Phase 5: LGSF/Canopus improvement shutdown
start shutdown at end of run #3
-Canopus descoped tasks
-Descoped tasks not required in future
design and build 2Fold Mirror Tip-Tilt mounts on pedestal (for Canopus-GSAOI coupling)
design and build flexure camera mount for flexure rig
-Flexure test and characterisation (on flexure rig)
install Canopus on flexure rig
Canopus flexure testing
Other flex and temp tasks
remove Canopus from flexure rig and set up on cart
+coupling and preps
-Descoped tasks required in future (shutdown)
OSL / AOM AT
Tip/Tilt drift - recheck effects and behaviour under different config and gravity vectors
+optical integration
+Sci BS MEG
+Sci ADC
+Sci ADC System Validation
+NGS ADC
+NGS ADC System Validation
AO verif: NGS ADC misc.
+Canopus-GSAOI integration
+Canopus improvements
-GS laser improvement shutdown (included in project ENG11-095: GN and GS laser ops reliability and efficiency improvements (R. Oram))
Milestone: GS laser shutdown start date (based on Canopus improvement shutdown start date)
Milestone: GS laser shutdown end date (based on Canopus improvement shutdown end date)
GS laser shutdown duration based on ENG11-095: GN and GS laser ops reliability and efficiency improvements (R. Oram)
end LGSF/Canopus hutdown and resume tech/science commissioning
-GeMS milestones
GM1: BTO ready for laser
GM2: laser system aligned and ready for BTO
GM3: Canopus installation on telescope
GM4: GSAOI installation on telescope
GM5: LGSF ready for commissioning run#1
GM6: LBBS commissionned
GM7: LGSF commissioning run#2
GM8: GeMS tech commissioning run#1
GM9: GeMS tech comissioning run#2
GM10: Gems tech commissioning #3
GM11: start LGSF/Canopus shutdown
GM12: end shutdown and resume tech/science commissioning run #4
+Management and documentation