## Recovered_Sheet1
OBS09-006C: GSAOI Data Reduction Software (SCI11-601)
Name
-Data Reduction Support for GSAOI
-GSAOI DR - 2011 Management
GSAOI DR - Project Management
-GSAOI Scheduling Milestones
GSAOI Producing Engineering Data
GSAOI On-Sky #1
GSAOI On-sky #2
GSAOI Commissioning Completed
GSAOI SV Starting
F2 DR Imaging Software Available
-GSAOI 2011 DR Deliverables Milestones
GSAOI DR - Requirements Completed
GSAOI DR - Acquisition Script Completed
GSAOI DR - CL DR Scripts Completed
-GSAOI DR - 2011 Meetings
GSAOI DR - Kick-off meeting
GSAOI DR - Coordination meeting
GSAOI DR - Project wrap-up meeting
-GSAOI DR - Requirements
GSAOI DR - Flowcharts
GSAOI DR - Scientific Requirements Document
GSAOI DR - Requirements for DR Completed
-GSAOI DR - Data Gathering
GSAOI DR - Obtain full data set for broadband
GSAOI DR - Obtain full data set for narrowband
GSAOI DR - Test data in hand
-GSAOI DR - CL Commissioning Scripts
-GSAOI DR - Complete commissioning scripts for release
GSAOI DR - Standardize commissioning scripts
GSAOI DR - Mosaic routine
GSAOI DR - Other essential routines TBD from requirements
GSAOI DR - CL DR scripts completed
-GSAOI DR - Testing
GSAOI DR - Write RTF unit tests
GSAOI DR - Write RTF end-to-end test
GSAOI DR - Run all the RTF tests
GSAOI DR - RTF tests for CL DR completed
-GSAOI DR - Documentation
GSAOI DR - Write IRAF help pages for each task
GSAOI DR - Documentation for CL DR completed
GSAOI DR - CL Support Completed
-GSAOI DR - Acquisition Script
GSAOI DR - Modify gacq to support GSAOI
GSAOI DR - gacq on-sky verification
GSAOI DR - Finalize gacq support for GSAOI
GSAOI DR - Write RTF tests for gacq with GSAOI
GSAOI DR - gacq is ready
-De-scoped from 2011
GSAOI DR#1 - Launch Python DR Cycle 1
GSAOI DR - Make commissioning scripts run in PyRAF
+GSAOI DR - 2012 Management
+GSAOI DR - 2012 Meetings
+GSAOI Python DR - Cycle 1
+GSAOI DR - Acceptance Tests
GSAOI DR - DR Software Ready for Release
GSAOI DR - 2012 Contingency
GSAOI DR - 2011 Contingency
GSAOI DR - Project Completed