## Recovered_Sheet1
OBS10-006A: GMOS New CCDs (J. White) (ENG10-004)
Name
-Phase 0: Project Planning
-General Project Planning and Project Initiation
+Project Initiation Meetings
+Project Planning Meetings
+Project Planning (Systems Support)
-Acceptance Test Preparations
Begin AT Preparations
Review HIA AT Plan
Revise/Amend AT Plan as Appropriate
AT Plan Ready
-Review Contract Deliverables and ICDs
Begin Review of Contract Deliverables and ICDs
Review Contract to Determine Actual Deliverables(including hardware/software/documentation/installation help) to Gemini
Send a summary to the Gemini GMOS-CCDs project group to assure HIA-Gemini alignment
Review of Contract Deliverables Complete
-Review, Develop internal docs and procedures
Begin Assessment, Development, and Review of Internal Documentation and Procedures
Assess current state of documentation and recommend areas of improvement
Mechanical Removal, Transportation, and Installation Instructions
Electrical Connections and Safeguards Documentation
Verification and Validation Documentation
Review Newly Created Documentation
Personel and Equipment Safety(including environmental concerns such as Humidity, Preventative measures for window cover...) Assessment
Assessment, Development and Review of Internal Documentation Complete
-Planning for Dewar Transition (Summit->HBF->Summit)
Planning for Dewar Transition
-Phase I: HBF Lab Controller Testing
-E2V Noise Characterization Assessment
Begin E2V Noise Characterization Assessment
Assemble and Analyze Saved E2V Noise Characterization Data
Assess If Additional Baseline Data Are Required
Acquire Additional Baseline E2V Bias Frames
Reduce and Analyze Additional Baseline Noise Data(Keep on Hand for Operational Tests of New CCDs)
E2V Noise Characterization Assessment Complete
-Preparations for Arrival of Hamamatsu CCDs
-Clean Room Preparations
Cleaning lab and tools
Purchase New Clean Room
Setup Clean Room
Installation of Tools and supporting infrastructure
-Detector Lab Preparations
-Software Preparations(FIXED DEADLINES)
-Data analysis Machine setup
Prepare Data Analysis Machine
-Observatory Software I&T
Install /test working Gemini sw envrt.
-Hardware Preperations
Test Lakeshore
Install Lakeshore at summit(earlier?)
-SDSU hardware preps
Configure / test working one-ch controller
Fiber optic switch for ARC65 resolution fix
-End-to-end Minimal System Test
Test machines and simulator verification using minimal system
-Supporting Integration and Testing Purchases
Thermostats
Spare Lakeshore controller
Optical Components for Optical Bench
Pump Cart
Flow Bench
-Controller boards and spares
Arc boards
30V power supply
-Mechanical Fixture for Microscopic observations of CCDs in FPA
Begin Mechanical Fixture work for Microscopic observations of CCDs in FPA
Identify Requirements and existing equipment for Microscopic observations of CCDs in FPA
Design Fixture for Safely and Accurately Measuring the Height of the CCDs in the FPA
Fabricate and Procure Fixture and Supporting Hardware
Receive and Assemble Fixture and Supporting Hardware
Validate the Safety of the System Before Using with Real CCDs
Mechanical Fixture for Microscopic Observations of CCDs in FPA Complete
-Summit Installation of Test Dewar Preparations
Begin Summit Installation of Test Dewar Preparations
Analyze Need for Installation of Test Dewar into GMOS at the summit
Prepare Installation Plan and Associated Documentation
-Mechanical Support Structure
Design Mechanical Support Structure for Test Dewar
Fabricate Mechanical Support Structure for Test Dewar
Assemble and Verify Mechanical Support Structure
-Electronic Connection, Cable Routing, and Power Support Planning
Design Electronics Installation and Cable Routing for Test Dewar Installation
Fabricate/Purchase any needed parts
Assemble and Verify Electronics Installation and Cable Routing Plan
-Optical Path Verification
Review Test Dewar installation Plan for Optical Path Encroachment
Summit Installation of Test Dewar on GMOS Preparations Complete
HBF Detector Lab Validated for Reception and Testing of GMOS CCDs
-Transition of GMOS CCDs from HIA to HBF Detector Lab
CCD System Departs HIA (Fixed Date)
CCD System Transit HIA -> HBF
CCD System Received and Stored at HBF in accordance with Transition Documentation
All HIA Equipment and Deliverables Safely in Detector Lab
-Test Dewar Prep & Initial Gemini SW integration
Begin Test Dewar Preparations
+Initial Checkout and Test Preparations
Test Dewar Ready for HBF Testing
+integrate HIA delivered hardware and SW with Gemini supplied SW and systems
+Full GMOS Test Functional Testing ( Minimal Modes )
+Full GMOS System Functional Testing ( Additional Modes and Summit Testing - If Required¦Time Permits )
+Full GMOS System Burn-in Testing Period
Ready to Remove GMOS from the Telescope
Science Scheduled Removal of GMOS from the Telescope
-Phase II: Integration of GMOS FPA/CCDs
+Remove GMOS and Transport
+GMOS Summit Tasks (+Maintenance Process)
-Install New FPA into Dewar - HBF Det Lab
Unpack GMOS Dewar
Remove E2V FPA
Obtain Initial microscopic height measurement of E2V CCDs in FPA
Store E2V FPA in safe
-Perform Dewar Modifications
Exchange Cold Heads
Remove Hamamatsu FPA from Test dewar
Verify Microscopic Measurements of new FPA in GMOS Dewar
Install new FPA into GMOS dewar
-Test New FPA (In GMOS dewar) - HBF Det Lab
-Warm Test of New FPA in GMOS Dewar
Warm Test Dewar using Engineering Interface
-Cold Test of New FPA in GMOS Dewar?
Pump down and Cool Dewar - Overnight
Cold FPA in Test Dewar using Engineering Interface
Dewar Ready for Detector Lab Testing
+Detector Lab Acceptance Testing
Ready to Transport dewar to summit
+Transport GMOS Dewar Back to MK
+Re-integration into GMOS
+Post-integration testing
-Phase III: Summit Operational/Acceptance Testing
-Summit Operational Testing and Acceptance Testing
-Integration of Dewar back into GMOS
Install Dewar
Install Thermal Enclosure
Pump down and Cool of GMOS (Docking Station)
-Dock testing?
Dock testing here if required
GMOS ready to be re-installed
GMOS scheduled installation from Science group
-Installation on Telescope
Install GMOS on Telescope using Written Procedures
-Daytime OT and software AT
Complete Daytime OT and Final Software AT
-Final On-sky OT and software AT
Complete Nighttime OT and Final Software AT
GMOS-N CCDs AT complete
-Phase IV: Science Commissioning Support
Engineering Support for Science Validation (Commissioning)
GMOS Ready for Queue
GMOS Scheduled for Queue from Science Group
GMOS new CCDs project Completed
+Project Milestones and FTEs(Original Project Plan)