## Recovered_Sheet1
OBS10-006B: GMOS-N CCD science commissioning (SCI10-244)
Name
Project Management/Communication (CCDs)
Engineering and Installation
-Software Commissioning
-ITC updates
SCI-0281 : Add new GMOS-N filters to the ITC
REQ-CCDSW-ITC-1
New OT Modes
Seqexec Modifications
IRAF data reduction software
GMOS DC updates
-GMMPS modifications
REQ-CCDSW-MDS-1
SCI-0281 : Add new GMOS-N filters to GMMPS
ISD updates
-Daytime Commissioning Tasks
Detector Flatness
Detector Baseline Measurements
Detector Dark Current
Nod&Shuffle Darks
IFU GCALflats and CuArs
Charge Transfer Checks
Pinhole Mask images for Transformations
Arcs and GCALflats
Charge Diffusion Test (RedFix)
Bias level stability
New ICD Nod&Shuffle Testing
-On-Sky Commissioning Tasks
On-sky Checks
Imaging mode, WCS determination
Spectral Absolute Throughputs
MOS mode commissioning
Fringing Characterization (Imaging and Spectral)
Contingency On-Sky RedFix Testing
Color Terms and Photometric Zero-Points
RTSW support
Systems Engineering Support
-Documentation and Webpages
Webpage update with Results
OT Libraries updates
GCALflat and CuAr Exposures Webpage
Present Results at Science Meeting