## Recovered_Sheet1
OBS10-006C: GMOS DR for new CCDs (SCI11-606)
Name
-Data Reduction Support for GMOS-N Red-Sensitive CCDs
GMOS CCD DR - Project Management
-GMOS CCD - Commissioning Milestones
CCDs in GMOS
GMOS Engineering data available
GMOS on-sky
GMOS-N CCD on-sky Commissioning Completed
-GMOS CCD - 2011 DR Deliverables Milestones
GMOS CCD DR - Acquisition script completed
GMOS CCD DR - CL DR scripts completed
-GMOS CCD DR - Meetings
GMOS CCD DR - Re-kick-off meeting
GMOS CCD DR - Coordination Meetings
GMOS CCD DR - Project wrap-up meeting
-GMOS CCD DR - Coding
Request full data sets (with correct headers and all)
Request data for gmosaic geometry and y-distortion for MOS cutting
Full GMOS data sets delivered
Data for geometric measurements delivered
Complete modifications to CL scripts and configuration files
Update gacq
Update odf2mdf
GMOS-N CCD DR - Coding Completed
-GMOS CCD DR - Testing
Create gacq tests
Create end-to-end reduction tests for img, ls, mos, ifu, n&s
Create unit tests
Run all the tests to confirm completion
Fix code based on test results
GMOS-N CCD DR - DR Software Fully Tested Completed
-GMOS CCD DR - Documentation
GMOS CCD DR - Update IRAF help pages
GMOS-N CCD DR - Documentation Fixes Completed
-GMOS CCD DR - Acceptance Test
GMOS CCD DR - DR tests by the SOS
GMOS CCD DR - Nighttime tests by the observer
GMOS-N CCD DR - AT Completed
GMOS-N CCD DR - DR Software Ready for Release
GMOS-N CCD DR - Contingency
GMOS-N CCD DR - Project Completed