## Sheet1
OBS10-007A: F2 Fixes and Improvements
Name
-F2 Fixes and Improvements
-Project Plan Manag and Support
Project Management
Group Coordination Meetings
Project Procurement
Decision on Modifying MOS F2 ColdSurface
Resources Assig Ops Affecting F2 Progress
-Preparation and Prerequisites
Prepare SBF Lab to receive F2
Prepare SBF Lab to service F2
Perform ENT to characterize OI for TTF and AO corrections
Drawing Readiness Analysis
Detector Mount thermal Study and Analysis
Contact UF to request SW assistance for ISD Implementation
Procure F2 insurance and NSF approval
Transportation Insurance Approved
Perform MOS Cold Foot Characterization
MOS and Camera Warm UP start
Remove F2 from Telescope
F2 Packing for Transportation
F2 Packed Ready for Transportation
CONTINGENCY (Being Used to Prepare Transpor)
Transport Instrument and Service Cart to SBF Lab
F2 Safely in the Lab
CONTINGENCY
F2 Ready to start disassembling
Preps for Camera Opening to reach GV Baffle
Prepare Lab He lines to Support F2
-MOS and OIWFS Fixes and Improvements
Disassemble and Inspect MOS cryostat
+MOS Analysis and Eng Re-Design
+OIWFS Work
-MOS Mechanisms Testing (Warm&Open)
MOS Wheel testing and tunning
MOS Decker testing and tuning
MOS (Camera) Cabling Checks
MOS Mechanisms Tested and Tuned
+MOS Dewar Assembly and Cold Testing
-Camera and GV Baffle Fixes and Improv
+Open Camera Cryostat for Inspections
-GV Baffle Improvement
GV Baffle Mech Engineering
GV Baffle Solution Available
GV Mech Shop Drawings
GV Commercial Parts Procurement
GV Parts Procurement lead time
GV new baffle Assembly and Tested
GV Baffle Improved
+Camera Improvements
-Det Replacement, Cam New Optics Inst and Alignment
Detector replacement Approach Analysis
Camera Optical Alignment Analysis and New Optics preps
Remove old detector (Mux or Old)
Install R3K grism
Install 2 new filters
New Optics in Place
New Detector Installation and checks
Optical Alignment Check
Camera and MOS Coupling
Camera and MOS Cooldown (Cycle 1)
Camera Cold (cycle 1)
Camera and MOS Functionality Test
New Detector Characterization
Camera and New Detector Characterized
Camera Cooldown (Cycle 2)
Camera Cold (Cycle 2)
CONTINGENCY
New Detector in place fully characterized
-F2 Software Pending Issues
Sync flam2sparc with repository
Make F2 software work on simulation in the lab
Make F2 software write header keywords on header unit 0 and 1
+WCS implementation
+FITS keywords
+Pixel router work
+Other Tasks and Contingency
+SCI Ops Software Modifications
-F2 Preps and Integration at CP Lab.
Camera and MOS warm up
Camera and MOS preparation to Ship
Transportation to CP
Full Reintegration in the CP Lab
Camera and MOS cooling cycle
F2 ready to be mounted to Flex Rig
Full Functionality Test at the Flex Rig
CONTINGENCY
F2 Ready for On Sky Re-commissioning