## Sheet1
OBS10-007B: F2 Science Commissioning
Name
-Flamingos-2 science commissioning
+Information 2010
-2010 Work
Flamingos-2 planning
+F2 fixing work on SBF
+Mask Making 2010
+OIWFS Functionality
Other Analysis of 2010 data
+Imaging 2010
-2011 Work
Planning
+H2 Characterization
-Flex-rig and Engineering support
flex-rig work
prep for flex-rig
analysis of flex-rig data
-AT preparation
Prepare sequences
daytime work
AT preparation analysis
prepare plan and update procedures
check scripts (gacq, goipos, gsfpos, focus)
check readiness prior to going on the sky: ALL SYSTEMS
installation on up-looking after flex-rig
-AT and Comm runs
on-sky AT Up
engineering support during up-looking port AT
installation on side-looking port from up-looking port
on-sky AT side
engineering support during side-looking port AT
engineering support during commissioning run I
engineering support during comm run II
engineering support during comm run III
Comm Run III
Comm Run II
Comm Run I
+OIWFS Commissioning 2011
-Imaging 2011
Imag Data Reduction software checks
Imag OT sequences plus target selection
Imag Daytime Data Processing
-Long Slit Commissioning 2011
LS Data Reduction Software checks
LS OT sequences plus target selection
LS Daytime GCAL and Arc OT sequences
LS acquisition script test
LS two object acquisition method
LS Blind offset acquisition
Analysis of LS commissioning data
-MOS commissioning 2011
Spectral Curvature MOS masks
MOS preimaging
MOS Data reduction checks
MOS OT sequences
Daytime data reduction from MOS
-MOS Checking
Design mask for science comm
Check Mask Design
-SV 2011
Prepare webpages plus documentation
software reduction checks
support call for proposals
SV observations
-Software support
support software work and debugging (ISD, Seqexec, AG, AGseq,FJEC)
ICTP work (science)
ICTP work (software)
+Documentation, meetings, and misc
Flamingos-2 ITC