## Sheet1
OBS10-007C: Data Reduction Software for Flamingos 2
Name | Duration
-Data Reduction Software for F2 | 681d
-F2 DR - 2011 Management | 248d
F2 DR - Project Management | 248d
F2 DR - Technical Coordination | 248d
F2 DR - Scientific Coordination | 248d
-F2 Scheduling Milestones | 101d
F2 Producing Engineering Data
F2 On-sky
F2 Commissioning Completed
DPD Ops - Patch release of CL scripts issued
-F2 DR - 2011 Deliverables Milestones | 8d
F2 DR - CL-only DR scripts ready for packaging & release
F2 DR - Python/PyRAF Cycle 1 DR scripts ready for packaging and release
-F2 DR - 2011 Meetings | 208d
F2 DR - Re-kick-off meeting
F2 DR - Coordination meetings | 247d
F2 DR - Project update meeting
-F2 DR - Data Gathering | 5d
F2 DR - Obtain full data set for Imaging | 5d
F2 DR - Obtain full data set for Longslit | 5d
F2 DR - Obtain full data set for MOS | 5d
-F2 CL work for Operations and early users | 42d
-F2 DR - gacq | 9d
F2 gacq - Implement support for MOS. | 3d
F2 gacq on-sky verifications | 2d
F2 gacq - Finalize support for MOS | 2d
F2 gacq ready
+F2 DR CL - Verifications on real data | 20d
-F2 DR CL - Testing | 4d
F2 CL - Write end-to-end MOS script | 2d
F2 CL - Final fixes | 2d
F2 CL - Tests completed
-F2 DR CL - Documentation | 8d
F2 CL - Help pages | 6d
F2 CL - Write example scripts based on end-to-end test scripts | 2d
F2 CL - Documentation completed
F2 CL - Ready for packaging and release
-F2 Python DR - Cycle 1 | 221d
-F2 DR#1 - Design
F2 DR#1 - S/W Design Completed
-F2 DR#1 - Development | 123d
+F2 DR#1 - Interfaces | 15d
-F2 DR#1 - Group 1 | 17d
F2 DR#1 - Slit tracing | 6d
F2 DR#1 - Cut out spectra | 6d
F2 DR#1 - Wavelength Calibration | 4d
F2 DR#1 - Group 1 Completed
+F2 DR#1 - Group 2 | 17d
+F2 DR#1 - Group 3 | 24d
+F2 DR#1 - Group 4 | 19d
+F2 DR#1 - Group 6 | 29d
F2 DR#1 - Cycle 1 Development Completed
-F2 DR#1 - Code Reviews | 104d
F2 DR#1 - Review preparation for PyRAF and shell interfaces | 2d
F2 DR#1 - Code review of PyRAF and Shell interfaces
F2 DR#1 - Review preparations Session 1 | 2d
F2 DR#1 - Code Review Session 1
F2 DR#1 - Review preparations Session 2 | 2d
F2 DR#1 - Code Review Session 2
F2 DR#1 - Review preparations Session 3 | 2d
F2 DR#1 - Code Review Session 3
F2 DR#1 - Review preparations Session 4 | 2d
F2 DR#1 - Code Review Session 4
F2 DR#1 - Review preparations Session 6 | 2d
F2 DR#1 - Code Review Session 6 | 1d
F2 DR#1 - Cycle 1 Code Reviews Completed
+F2 DR#1 - Testing | 139d
+F2 DR#1 - Documentation | 106d
F2 DR#1 - Cycle 1 Completed
F2 DR - 2011 Contingency | 67d
-De-scoped from 2011 | 433d
F2 DR - Scheduling Marker
+F2 DR - 2012 Management | 248d
+F2 DR - 2012 Meetings | 433d
-F2 Python DR - Cycle 1B | 29d
+F2 DR#1B - Development | 22d
+F2 DR#1B - Code Reviews | 3d
+F2 DR#1B - Testing | 5d
+F2 DR#1B - Documentation | 10d
F2 DR#1B - Cycle 1B Completed
+F2 Python DR - Cycle 2 | 229d
+F2 DR - Acceptance Test | 49d
F2 DR - DR Software Ready for Release
F2 DR - 2012 Contingency | 154d
F2 DR - Project Completed
681d