## Recovered_Sheet1
OBS11-003: GPI Observatory Project
Name
-GPI Observatory Project
-Pre-delivery Stage
+Stage Management and Coordination
System Engineering Interaction and Tracking of Operation Software
Internal 'Science Requirements' Work Package Responsibilities
Community Interaction
Data Analysis Tools and on-ste Data Reduction Pipeline KT
GPI Web Pages
+AO Techincal Meetings
-GIAPI/OCS Infrastructure
Mentoring
-Documentation tasks
GIAPI technical Manual
WCS ICD
-GIAPI Gemini APIs (ICD 1x-2)
-Gemini Status API
+Status Subscription support API
+EPICS JCAS Server Service
+EPICS Status Service
+EPICS Alarm Service
+EPICS Health Service
+Gemini Commands API
-GIAPI access to EPICS Systems
Configure and test TCS Context service
Configure and tests post PCS Update
Configure and test EPICS status monitoring functionality
[DOC] Update GIAPI Technical manual
Contingency
-Tested Reflective Memory Interface
Create test platform SCS/Synchro bus/GIAPI
Test communication and interruptions between GIAPI/SCS
Test mapping of RM in >4GB segments
Contingency
-GIAPI Data Service
+DHS Design Study
+FITS File Name Generation
+Health Publisher
+Instrument Configuration Management
+Keyword Provider Service
+Instrument Status Monitoring
+OCS Status Monitor
+Telescope Status Monitoring
+Observation Event Handlers
+FITS Header Update functionality
+Administration Service
+Quick Look Tool Interface
-GEA interface to GIAPI
Define Test Plan
Execute Tests
-GIAPI to Engineering Screens
-API to send engineering commands to instrument via GIAPI
Create OSGI bundle
Define extended functionality to add to the Commands API
Extend Status API
Create Validation Engineering Screen for testing
Write unit tests
Take perfromance measurements
[DOC] Update GIAPI technical manual
-Add support for additional languages (Phython?, others)?
Identify Target language (trade study)
Implement JMS integration service for new language
Create test application to test JMS integration
Test JMS integration
Implement Engineering Command API
Implement Test Application using command API
Refine Engineering Command API
Write Unit Tests
[DOC] Update GIAPI technical manual
Contingency
-GPI/OCS Science Tasks
+Definition Phase
+Commissioning Work Packages
+Final Work Packages
-Gemini South Preparation Work Package
+Clean Room Extension Activity (4.8m x 3.5m x 2.2m) - class 1000
+Clean Room Supplies
+Tweeter Mantainence
+Vacuum pump accessability
+Spares/Storage Cabinet
+Standard Lifting Equipment
+GPI Toolbox
Ensure toolbox contains: Allen keys (metric)
Ensure toolbox contains: Allen Socket Drives (Metric)
Ensure toolbox contains: Combination Wrenches (Metric)
Ensure toolbox contains: Torque Wrench
+Expendables
+Working Table
+GPI Equipment Storage Area
+Specialized Tools
IS Preparation
+Instrument I&T Phase (Vendor Oversight)
+On-site Acceptance Stage
+Science Verification and Commissioning Stage
+Project Milestones