## Recovered_Sheet1
OBS11-005: 2nd Generation Acquisition and Guidance Unit Observatory Project
Name
-2nd Generation Acquisition and Guidance Unit Observatory Project
-Stage 1 - Instrument Requirements
Stage 1 Duration is 3 months
-Stage Management
Stage Oversight
+Project Management Team Meeting
+Stage Planning
+Risk Management
-A&G Existing Capabilities
-Review Exisiting A&G Documentation
Obtain 1st Gen. A&G Units Request for Proposals
Obtain 1st Gen. A&G Units Proposals
Obtain 1st Gen. A&G Units Requirements Documents
Obtain 1st Gen. A&G Units Test Report
Review Obtained Documentation
Extract Requirements from documentation
-Review A&G Requirements from Instrumentation
Identify Source of Information (i.e. Instrument User Manuals)
Read Instrumentation User Manual
Extract Requirements based on operational instrumentation
-Write Report
Draft Report
Circulate Report for internal review
Review Report
Update and release final version
-A&G Future Capabilities
-Reasearch into possible future capabilities
Understand the requirements of future instrumentation based on insturment roadmap
Obtain Gemini GLAO Report, review and extract requirements
-Write Report
Draft Report
Circulate Report for internal review
Review Report
Update and release final version
-Quality / Workmanship Requirements
-Review Gemini Quality Expectations relating to Interfaces and Workmanship
Review/Define Existing Engineering Quality/Workship documentation
Obtain & Read existing Gemini A&G ICD
Extract/form requirements based on Gemini's Quality / Workmanship Expectations
-Write Report
Draft Report
Circulate Report for internal review
Review Report
Update and release final version
-Review Operations of the existing A&G
-Conduct FMEA Analysis
Review previous A&G Faults contained in database
Hold 360 feedback review of staff experience with existing A&G with emphasis on improving reliability
Extract Requirements from process
-Write Report
Draft Report
Circulate Report for internal review
Review Report
Update and release final version
-Instrument Requirements Document
Produce document outline and Table of Contents for Instrument Requirements Document
Extract Requirements from 4 research reports
Write Draft IRD
Circulate for comments
Modify and release
-Project Approach and Contract Preparation
Conduct analysis regarding the possible options for outsourcing work
Discuss options with Contracts Manager
+Write Report
-Stage Review
Programme Board review stage 2 plan, IRD and Outsourcing Approach document and commit resources for next stage
-Stage 2 - Request for Proposals
Stage 2 Duration is 6 months
-Stage Management
Stage Oversight
+Project Management Team Meeting
+Stage Planning
-Place call and Select 2 Vendors to conduct Preliminary Design
Prepare bizops material
Make BizOps announcement
Prepare Request for proposals
Submit Request for proposals
Answer questions related to call for proposals
Make preparations regarding the selection process
Recieve and Review Proposals (which will contain a conceptual design)
Vendor Selection - select 2
Negotiate Contracts with go vendors
-Stage Review
Programme Board review stage 3 plan and contracts
Sign Contracts
-Stage 3 - Preliminary Design
Stage 3 is to be tasked and resourced during Stage 2
-Stage 4 - Critical Design
Stage 4 is to be tasked and resourced during Stage 3
-Stage 5 - Final Design
Stage 5 is to be tasked and resourced during Stage 4
-Stage 6 - Fabrication
Stage 6 is to be tasked and resourced during Stage 5
-Stage 7 - Integration & Test
Stage 7 is to be tasked and resourced during Stage 6
-Stage 8 - On-site Acceptance Test
Stage 8 is to be tasked and resourced during Stage 7
-Stage 9 - Post delivery Acceptance Test
Stage 9 is to be tasked and resourced during Stage 8
-Stage 10 - On-sky verification and Commissioning
Stage 10 is to be tasked and resourced during Stage 9
+Project Milestones (TO BE COMPLETED)