## OBS11-501 Base Facility Operati
OBS11-501 Base Facility Operations (M. Sheehan)
Name
-Remote Operations
-Project Management
Project kick-off
Project Lead/System eng meetings
Definition of Requirements
Project planning
Definition of Risk Ledger
General Systems Engineering
ICD Generation and review
Risk Management
-Conceptual Design Phase
-Comprehensive Review of Observatory Systems
kickoff subsystem review
-Telescope Systems
-Telescope subsystems
Mount and MCS
M1 and PCS
M2 and SCS
Elevation Cable Wrap
Azimuth Cable Wrap
Cassegrain Rotator Cable Wrap
Elevation Encoding System
Azimuth Encoding System
Mirror Covers
Locking Pins
A&G Unit
GCAL
GIS/LIS
Telescope Control System
Cass Rotator Control System
+OCS
+Weather Monitor system
+Instrument Systems
+Laser Guide Star Facilities
+Enclosure Systems
+Facility Systems
+Network and Communications Systems
-Failure Modes and Effects Analyses
Telescope Systems
Cassegrain and Instrument Systems
Laser Guide Star Facilities
Enclosure Systems
Facility Systems
Network and Communications Systems
+BFO Initial Trials
-Define Subsystem Design Requirements
Telescope Systems
Cassegrain and Instrument Systems
Laser Guide Star Facilities
Enclosure Systems
Facility Systems
Network and Communications Systems
-Remote Operations Conceptual Designs
Telescope Systems
Cassegrain and Instrument Systems
Laser Guide Star Facilities
Enclosure Systems
Facility Systems
Network and Communications Systems
-Conceptual Design review
Telescope Systems Documentation
Cassegrain and Instrument Systems Documentation
Laser Guide Star Facilities Documentation
Enclosure Systems Documentation
Facility Systems Documentation
Network and Communications Systems Documentation
CoDR
CoDR Completed
-Preliminary Design Phase
-Remote Operations Preliminary Designs
Telescope Systems
Cassegrain and Instrument Systems
Laser Guide Star Facilities
Enclosure Systems
Facility Systems
Network and Communications Systems
Earthquake Safety Systems
Remote Lighting Systems
Remote Microphone Systems
Remote Camera Systems
-Subsystem Preliminary Design review
Telescope Systems
PDR Telescope System completed
Cassegrain and Instrument Systems
PDR Cassegrain and Instrument Systems completed
Laser Guide Star Facilities
PDR Laser Guide Star Facilities completed
Enclosure Systems
PDR Enclosure Systems completed
Facility Systems
PDR Facility Systems
Network and Communications Systems
PDR Network and Communications Systems
-Detailed Design Phase
-Remote Operations Detailed Designs
Telescope Systems
Cassegrain and Instrument Systems
Laser Guide Star Facilities
Enclosure Systems
Facility Systems
Network and Communications Systems
Earthquake Safety Systems
Remote Lighting Systems
Remote Microphone Systems
Remote Camera Systems
-Subsystem Critical Design Reviews
Telescope Systems
CDR Telescope System completed
Cassegrain and Instrument Systems
CDR Cassegrain and Instrument Systems completed
Laser Guide Star Facilities
CDR Laser Guide Star Facilities completed
Enclosure Systems
CDR Enclosure Systems completed
Facility Systems
CDR Facility Systems
Network and Communications Systems
CDR Network and Communications Systems
-Procurement Phase
-Procurement and Fabrication (GN & GS)
Telescope Systems
Cassegrain and Instrument Systems
Laser Guide Star Facilities
Enclosure Systems
Facility Systems
Network and Communications Systems
Earthquake Safety Systems
Remote Lighting Systems
Remote Microphone Systems
Remote Camera Systems
-Integration and Test at MK
Telescope Systems
Cassegrain and Instrument Systems
Laser Guide Star Facilities
Enclosure Systems
Facility Systems
Network and Communications Systems
Earthquake Safety Systems
Remote Lighting Systems
Remote Microphone Systems
Remote Camera Systems
I & T at MK Completed
-MK Base Facility Operations Trial Period
Nighttime Tech Support
Hand-Over for Remote Operations at MK
-Integration and Test at CP
Telescope Systems
Cassegrain and Instrument Systems
Laser Guide Star Facilities
Enclosure Systems
Facility Systems
Network and Communications Systems
Earthquake Safety Systems
Remote Lighting Systems
Remote Microphone Systems
Remote Camera Systems
I&T at CP Completed
-CP Base Facility Operations Trial Period
Nighttime Tech Support
Hand-Over for Remote Operations at CP