## OSW11-200 ITAC Phase 2 (D. Daws
Name | Duration
-Requirements Stage | 250d
Solicit and digest available information
Systems engineer effort | 2d
Identify requirements
Prioritize requirements | 2d
Identify constraints
Create UI mockups | 5d
Document requirements | 3d
Create testing procedure | 2d
ITAC Phase 2 user review and testing | 294d
-Requirements Milestones | 555d
-Essential | 126d
FR-02 - Multiple access roles.
FR-04 - Multiple access windows
FR-06 - Integrated Gemini NTAC
FR-07 - Integrated LPTAC.
FR-27 - Distributed ITAC Process
FR-39 – Access control
+Highly desirable | 485d
+Desirable | 447d
+Unprioritized
+Removed
-Scheduled Iterations | 555d
+Iteration skeleton
Project Kickoff
-Phase A - Azure Arrow - 3E/1D | 96d
Kickoff
-Gemini NTAC | 95d
Design workflow | 11d
Implement prototype workflow | 11d
Proposal import | 7d
Proposal display | 9d
Proposal commenting | 9d
Proposal statistics | 7d
Proposal sorting | 7d
Manual ranking editing | 3d
Manual comment editing | 2d
Manual recommended hour editing | 2d
Final approval | 7d
Export to ITAC | 8d
Testing NTAC system | 11d
End of NTAC
-Roles | 50d
Design role based permissioning system | 7d
Design interaction between window and role permissioning | 6d
Implement role based permissioning system | 7d
Program Administrator permissions | 6d
Test role based permissioining system | 7d
Technical Secretary permissions | 1d
ITAC Chair permissions | 1d
Gemini NTAC Chair permissions | 1d
Large Program TAC Chair permissions | 1d
Gemini NTAC Reviewers permissions | 1d
NTAC Partner permissions | 1d
ITAC Representatitive permissions | 1d
Head of Science Operations permissions94 | 1d
Test roles and permissions | 2d
End of roles
-Access windows | 18d
NTAC Comment Editing | 2d
ITAC comment editing | 2d
Contact scientist editing | 2d
NGO contact email editing | 2d
General program editing | 2d
Program change highlighting | 7d
End of access windows
-Joint merging | 26d
Identify requirements | 3d
Prioritize requirements | 1d
Prototype merge | 7d
Refine prototype | 7d
Identify additional requirements | 1d
Prioritize additional requirements | 1d
Implement additional requirements | 7d
End of joint merging
End
+Phase B - Baked Bug - 1E/1HD | 59d
+Phase C - Comfy Couch - 1E / 1HD | 33d
+Phase D - Damp Dandelion - 3 HD/1D | 77d
+Phase E - Eager Ermine - 3D | 40d
+Phase F - Free Fence - 2D | 55d
+Phase G - Giant Goon - 1D | 194d
+Task Backlog
+Contingency | 84d
-Information Systems Support | 250d
IT Support 2011 | 250d
IT Support 2012 | 250d
680d