## OSW11-201 Time Accounting Timel
OSW11-201 Time Accounting Timeline (S. Walker)
Name
-Time Accounting Timeline Project
-Evaluation Phase
Define Business Case
Kick off meeting
-Conceptual Definition Stage
Digest available Information
Identify User Needs
Prioritize User Needs
Systems engineer effort
Identify Contstraints
Create initial UI mockups
Document User Needs
Information System Support
-Elaboration Phase
Review and Update baseline requirements document
Initial Requirements Document
Create draft test procedures
Initial Test Plan
Identify Products
Produce high-level design/architecture
Create initial features list
Initial Features/Bug List
Prioritize Features/Bug list for iteration 1
Research implementation options
Perform initial prototyping
Make initial technology selections
Define testing/deployment platform
Setup testing environment
Update plan in PI
-Implementation Phase
-Software Iteration 1
Planning Meeting
Prioritize Features/Bug list for iteration 2
Update Requirements document for iteration
Update testing plans for iteration
Development Tasks
Scientist support
Iteration 1 Documentation
Iteration Review/QA meeting
Generate Release 1
Release 1
+Software Iteration 2
-Software Iteration 3
Planning Meeting
Update Requirements document for iteration
Update testing plans for iteration
Gather user feedback from release 2
Update features/bug list
Prioritize Features/Bug list for iteration 4
Development Tasks
Scientist support
Iteration 3 Documentation
Iteration Review/QA Meeting
Generate Release 3
Release 3
+Software Iteration 4
+Software Iteration 5
+Software Iteration 6
+Final Iteration
-Final User Acceptance Tests
Review of testing procedures
User's acceptance testing
Bug fixes
Generate Final release
Deploy final release
Contingency reserve