## OSW11-203 Queue Visualization (
OSW11-203 Queue Visualization (D. Dawson)
Name
-Queue Visualization
-User Requirements Gathering
Define Business Case
Science requirements documentation
Systems engineer effort
Placeholder for science effort
User requirements baseline document
-Evaluation Phase
Read User Requirements baseline document
Kick off meeting
-Conceptual Definition Stage
Digest available Information
Identify User Needs
Prioritize User Needs
Identify Constraints
Create initial UI mockups
Update User Requirements Document
Updated User Requirements Document
-Elaboration Phase
Review and Update baseline requirements document
Identify Products
Produce high-level design/architecture
Create initial features list
Initial Features list
Create plan in PI
Review plan
Information Systems Suport
Queue Visualization Plan in place
-Project Management
Project Management Tasks and coordination activities
Contingency reserve