## Sheet1
SCI11-620: QA Pipeline
Name
-QA Pipeline - Engineering Phase
+Summary of Top-Level Milestones
-2011 Meetings
Weekly Project Mtg
Project Management Mtg
Project Schedule Management & Day-to-day coordination
+2011 Science Working Group
+2011 Management Tasks
-Design/Development - Prep for CDR
+Planning
+Core Software Design & Development
+Prototyping Tests
-Summit Installation Design
Setup test Linux environment
Software benchmarking
Generate production design plan
Peer/Group review
+Critical Design Review
+Final Development
+I&T Execution
+Acceptance Test Execution
+Deployment
Completion of Phase 1 Milestone
-QA Pipeline Scientific Phase
+Planning for QA Modes
-New Features for Recipe System
-AstroData Structures
Structures System Design
Integrate Structures and AstroDataTypes systems
+New Features for PRS Components
-Design and Development of QA Modes
-QA Pipeline Optical Longslit Development
Launch of QA Optical Longslit Development
-Finalize Calibration Rules QA Optical Longslit
GMOS Longslit Calibration Rules
Calibration Rules for QA GMOS Longslit Calibration Completed
-Recipes for Optical Longslit Spectroscopy
-Recipes Design - Optical Longslit
Catalog Optical Longslit observation sequences
GMOS longslit flow charts
GMOS longslit "Walkthrough" document
GMOS longslit QA recipes design completed
-Recipes Development
GMOS longslit QA Recipes
Recipes for QA GMOS longslit Completed
-Star Catalogues
Selection of Star Catalogues
Star Catalogue ICD
Implementation of Star Catalogue Access Interface
-Primitives for Optical Longslit
-Data Reduction Primitives
Optical Primitives - Full list TBD
Optical longslit data reduction primitives completed
-Calibration Requests Primitives
Optical Primitives - storeProcessedArc
Optical Primitives - getProcessedArc
Optical longslit calibration request primitives completed
+Bookkeeping Primitives
+Metrics Primitives
Optical longslit metrics primitives completed
Primitives for optical longslit completed
+Packaging
QA Pipeline Optical Longslit Development Completed
+QA Pipeline Optical MOS Development
+QA Pipeline Optical N&S Development
+QA Pipeline Near-IR Imaging Development
+QA Pipeline Near-IR Longslit Development
+QA Pipeline Near-IR X-Dispersed Development
+QA Pipeline Near-IR MOS Development
+QA Pipeline Optical IFU Development
+QA Pipeline Near-IR IFU Development
+QA Pipeline Near-IR ASDI Development
+QA Pipeline Mid-IR Imaging Development
+QA Pipeline Mid-IR Longslit Development
+QA Pipeline Mid-IR IM Polarimetry Development
-I&T of QA Modes
-I&T for QA Pipeline Optical Longslit
Launch I&T for QA Optical Longslit
Revisions to I&T Plan for QA Optical Longslit
Set up integration environment
-Prepare for Integration Tests
Prep. Integration Tests - TEST TDB FROM PLAN
-Integration Tests - Standalone Context - QA Optical Longslit
Run Int.Tests Standalone QA Opt LS - TBD FROM PLAN
-Integration Tests - PRS Context - QA Optical Longslit
Run Int.Tests PRS QA Opt LS - TBD FROM PLAN
Integration Milestone QA Opt LS #1 - Completed
I&T for QA Optical Longslit Completed
+I&T for QA Pipeline Optical MOS
+I&T for QA Pipeline Optical N&S
+I&T for QA Pipeline Near-IR Imaging
+I&T for QA Pipeline Near-IR Longslit
+I&T for QA Pipeline Near-IR X-Dispersed
+I&T for QA Pipeline Near-IR MOS
+I&T for QA Pipeline Optical IFU
+I&T for QA Pipeline Near-IR IFU
+I&T for QA Pipeline Near-IR ASDI
+I&T for QA Pipeline Mid-IR Imaging
+I&T for QA Pipeline Mid-IR Longslit
+I&T for QA Pipeline Mid-IR Imaging Polarimetry
-AT of QA Modes
-AT for QA Pipeline Optical Longslit
Launch AT phase for QA Optical LS
Set up AT environment & assemble AT team
AT - QA Optical Longslit - Collect data
AT - QA Optical Longslit - Execute AT
AT - QA Optical Longslit - Document test results
AT - QA Optical Longslit Accepted
+AT for QA Pipeline Optical MOS
+AT for QA Pipeline Optical N&S
+AT for QA Pipeline Near-IR Imaging
+AT for QA Pipeline Near-IR Longslit
+AT for QA Pipeline Near-IR X-Dispersed
+AT for QA Pipeline Near-IR MOS
+AT for QA Pipeline Optical IFU
+AT for QA Pipeline Near-IR IFU
+AT for QA Pipeline Near-IR ASDI
+AT for QA Pipeline Mid-IR Imaging
+AT for QA Pipeline Mid-IR Longslit
+AT for QA Pipeline Mid-IR Imaging Polarimetry
-Deployment of QA Modes
-Deployment of QA Optical Longslit
Launch Deployment of QA Optical Longslit
Deployment - Ensure pre-requisites from other groups are met
Deployment - QA Opt LS - TBD FROM DEPLOYMENT PLAN
Deployment - QA Opt LS - Final documentation release
Deployment - QA Opt LS - Training
Deployment of QA Optical Longslit Completed
+Deployment of QA Optical MOS
+Deployment of QA Optical N&S
+Deployment of QA Near-IR Imaging
+Deployment of QA Near-IR Longslit
+Deployment of QA Near-IR X-Dispersed
+Deployment of QA Near-IR MOS
+Deployment of QA Optical IFU
+Deployment of QA Near-IR IFU
+Deployment of QA Near-IR ASDI
+Deployment of QA Mid-IR Imaging
+Deployment of QA Mid-IR Longslit
+Deployment of QA Mid-IR Imaging Polarimetry